+

| Project Plan – Rugby World Cup Legacy Program |  |  |
| --- | --- | --- |
| Project Plan | - Deliver a lasting legacy for NSW from the RWC 2027. |  |
| 01/05/2025 | sport.nsw.gov.au |  |

Contents

Overview project details	2

Project Description	2

Project Primary Beneficiaries	2

Project Outcomes	3

Project Deliverables	4

Performance Measures	5

Project Plan	9

Pillar 1: Facilities and Equipment	9

Pillar 2: Priority Regions & Pathways	9

Pillar 3: Programs & Workforce	10

Pillar 4: Inclusion	11

Pillar 5: RWC Activation	13

Project Management, Monitoring & Evaluation	13

Project Budget	14

Appendix	16

# Overview project details

## Project Description

This project aims to develop capacity and capability throughout the Rugby network whilst removing barriers to participation for a sustainable future. Innovative program development across play, infrastructure, workforce, and connecting with diverse communities will create opportunities, improve experiences, change perceptions and capture interest brought by the Rugby World Cup.

Pillar 1: Facilities and Equipment

Improving the places where people play Rugby and improving the development and safety of players across the game of Rugby in NSW.

Pillar 2: Priority Regions & Pathways

- RA together with NSWRU and ACT/SNSWRU intend to make targeted investment into priority regions across NSW that are either under-serviced or provide a strategic opportunity relative to other areas of NSW. It is a strategic initiative aimed at revitalising or increasing Rugby Union in these areas, boosting community engagement, driving participation and performance outcomes, and aligning with broader national objectives to grow the game of Rugby.

Pillar 3: Programs & Workforce

- Increasing opportunities by enabling more people to get involved in Rugby as a player, coach, match official or administrator, and increasing their access to development pathways. Supporting the Rugby workforce to deliver on their responsibilities, maximise retention, and create safe and inclusive environments for all involved in community Rugby in NSW.

Pillar 4: Inclusion

- Rugby Australia and its Member Unions are striving to ensure that Rugby is a place where every individual feels valued and has the opportunity to participate. By establishing meaningful collaborations, promoting a culture of mutual understanding, encouraging broader community involvement and enhancing knowledge and skills, Rugby Australia aims to embed inclusion at the heart of the sport.

Pillar 5: RWC Activation

- Leveraging the excitement and promotion generated by the Rugby World Cup to facilitate the long-term sustainable growth of Rugby across NSW.

## Project Primary Beneficiaries

Rugby Players

Rugby Coaches, Officials, Volunteers etc

Rugby Clubs

Schools

Local communities

## Project Outcomes

Pillar 1: Facilities and Infrastructure

- Improve the quality and accessibility of facilities, creating safer, welcoming and more inclusive environments. Resulting in higher recruitment and retention rates, with a particular emphasis on key inclusion groups, such as women and girls, and people with a disability.

- Improve access to scrum machines and key safety equipment, creating a safer environment for Rugby, reducing the risk of injury.

Pillar 2: Priority Regions & Pathways

- Invest time and resources into Western Sydney, creating opportunities to play Rugby in a format appropriate to the needs of the community.

- Rugby is a ‘sport of choice’ for young people in Western Sydney, as defined by the LGA’s of Canterbury-Bankstown, Blacktown, Cumberland, Liverpool, Fairfield, Penrith, Parramatta, The Hills, Campbelltown, Camden, Blue Mountains, Hawkesbury and Wollondilly.

- Use Rugby as a vehicle for change in the Hunter, lowering the resistance barrier to key social issues. In turn, this increases Rugby participation, but more importantly, addresses factors such as mental health, wellbeing, physical activity levels and education

- Invest in infrastructure, programs, pathways, inclusion and community engagement in the South Coast and Riverina, creating:

  - Improved accessibility making Rugby available to more people in the South Coast and Riverina

  - Talent through improved facilities, pathways and support programs

  - Strengthened Rugby clubs and the wider community through community cohesion and pride

  - Increased economic activity and engagement by bringing Rugby events and opportunities to regional NSW

- NB: Whilst Western Sydney, Hunter, and South Coast/Riverina are called out, investment will be made across the entirety of NSW in facilities, programs, workforce, inclusion and the Rugby World Cup activation

Pillar 3: Programs & Workforce

- Lower the financial, operational and logistical barriers to launching and expanding competitions and programs. Doing so will improve accessibility, increase engagement, drive sustainability in workforce across coaches, match officials, strengthen clubs and drive sustainable participation across NSW. Successful applicants will be required to demonstrate how this funding will be used in a sustainable manner and how the competition and programs will continue to grow and expand beyond the investment period.

- Increase the support and development of the Rugby workforce. Doing so, with a focus on coaches, match officials and club administrators, will deliver higher quality, safe, enjoyable Rugby experiences that ultimately safeguard and future proof the sport.

- Increase the quality and number of match officials and coaches. Doing so will improve the relationship between them and players, which will improve the playing experience, ultimately increasing player retention and recruitment.

- Investment into programs and workforce will be spread across metro and regional NSW.

Pillar 4: Inclusion

- Increase the training and opportunities for underrepresented groups in both participation and leadership positions, with a focus on women and girls, Pasifika and First Nations communities, building a culture of inclusion across Rugby.

- Invest in growth of the women’s game across the board, from inception through to coaching and match officials. Doing so increases the opportunities for women to take part in the sport.  Normalising women in Rugby improves attitudes towards inclusion and diversity creating a virtuous cycle of growth and retention

- Increase support for First Nations and Pasifika groups across leadership roles, talent ID, pathways and participation.  Increasing representation across pathway programs, and leadership and administration positions including coaches, match officials and administrators

- Embed a culture of safety, safeguarding and integrity into Rugby. By doing so, we will create safer environments, empower clubs, build trust across the game and community, enhance compliance, and safeguard the future of Rugby.

- Investment into inclusion programs and initiatives will be spread across metro and regional NSW.

Pillar 5: RWC Activation

- Capture the interest generated by the Rugby World Cup while it is at its peak. Doing so engages new participants and prepares the Rugby network and community to take advantage of the interest in the game and prepare them to capture new participants and deliver a great experience that provides a lasting impact in the sport.

- Rugby World Cup a

## Project Deliverables

Pillar 1: Facilities and Infrastructure

  - NSW Rugby infrastructure grants program

  - NSW Rugby equipment grants program

  - Infrastructure upgrade to Connolly Park in Wagga Wagga

  - Infrastructure upgrade to one priority facility identified in Sydney

Pillar 2: Priority Regions & Pathways

  - Launch Western Sydney Academy

  - New schools’ competition in Western Sydney

  - Create Rugby for Good Hub in the Hunter

  - Rugby for Good programs in the Hunter

  - Focused programs and support in the South Coast & Riverina

Pillar 3: Programs & Workforce

  - NSW Rugby Competition/Program grants program

  - Yearly Workforce Leadership Conference for Coaches, Match Officials and Administrators

  - Regional Get into Rugby Hubs

  - Regional Match Official support and development programs

Pillar 4: Inclusion

  - First Nations Talent ID program

  - First Nations Development Academy

  - NSWRU RAP

  - New female competitions in NSW

  - Female ‘Rising Star’ talent combines in Southern NSW

  - Female Coach Development Program

  - Female ‘Confidence in Contact’ tackle-ready programs

  - Pasifika Leadership Program

  - New competitions to enhance the playing experience for key inclusion groups

  - Integrity and safeguarding club support programs

Pillar 5: RWC Activation

  - RWC Event Hubs delivering Get into Rugby, Tri Tag Rugby, and introductory Coaching and Match Official programs

## Performance Measures

- Data & Measurement:

- All participation data measured in RA registration platform RugbyXplorer, visualised in Tableau and measured against RA yearly census – includes player numbers, coaches, match officials, administrators, # of matches played, coach and match official ratios.

- Compliance data measured in RA Club Health Check and measured against the RA Club Standards program

- Satisfaction ratings measured annually in RA End of Season survey

- RA to engage PhD student to analyse club health and viability pre- and post-funding period.

- RA to engage researcher to determine impact of priority region investment on the health of Rugby in Western Sydney, Hunter and South Coast/Riverina regions (note RA has already undertaken this work for Western Sydney in 2024/25)

- RA to engage agency to quantify the social value of Rugby and the social impact of the Legacy investment on Rugby in NSW. This will include a social impact framework and quantify the social impact of Rugby across NSW.  The work will be done at the commencement of Office of Sport funding and again post the Rugby World Cup to quantify any changes brought about by the Rugby World Cup and subsequent investment in NSW.

- Pillar 1: Facilities and Infrastructure

- 20 facilities to receive funding that addresses improved lighting, changerooms and/or sustainable practices

- Number of matches that are not impacted by rain (see RA audit data) – decrease YoY in areas with infrastructure investment

- Participation increases in facilities receiving infrastructure funding is greater than state and national average

- Amount of co-investment secured from local councils, partners and community clubs

- Deliver 2 x larger scale facility upgrades for identified priority facilities in NSW

- >20 clubs receive large scale equipment investment*

  - *Equipment will require co-funding.  Recommended scrum machines are ~$11,000 (excluding GST)

Pillar 2: Priority Regions & Pathways

- Western Sydney

- Increase regular club participation in W. Sydney by 2% per annum – baseline 4,729

- Increase overall participation by 7.5% per annum – baseline 6,127

- Head of Western Sydney

- Western Sydney Rugby alliance that meets 3 x annually

- New schools’ competition incl. Western Sydney Waratah Shield Division, U16 competition, and primary school competition for boys and girls and foster links between schools and local clubs

- Launch Western Sydney academy – 30 males and 30 females in the program per season

- Increase Western Sydney funding through Rugby for Good hub – source $125k annually

- Club Development

- Ensure all clubs in Western Sydney reach Developing standards in the RA Club Standards program and are all legally compliant organisations

- Club Development Manager to meet all clubs in Western Sydney twice annually

- Each Western Sydney club to complete the RA Club Health Check annually

- Each club to receive a tailored Club Action Plan

- Drive increase in gender balanced club boards (40:40:20) - 40% of clubs currently meet this ratio

- Reduce participant churn by 1% per year - baseline 48.9% in Western Sydney

- Western Sydney Development Officer

- Increase overall participation by 7.5% per annum – schools, clubs, gala days, tournaments

- Deliver 3 x coaching courses per annum

- Attend club training sessions 2 x per annum

- Reduce participant churn by 1% per year - baseline 48.9%

- Hunter

- Increase participation by 7.5% annually across all metrics – clubs, schools, coaches, match officials and administrators – baseline 3,290

- Source additional revenue opportunities via Rugby for Good programs – source >$100k annually

- Ensure all clubs in the Hunter reach Bronze/Developing standards in the RA Club Standards program and are all legally compliant organisations

- Each Hunter club to complete the RA Club Health Check annually

- Each club to receive a tailored Club Action Plan

Pillar 3: Programs & Workforce

- Competition Seed-Funding Grants Program

- Fund 20+ competitions/programs across NSW

- Increase participation by 7.5% annually across all metrics – clubs, schools, coaches, match officials and administrators – baseline of 113,429 participants

- >50% of funding to support female programs / competitions

- Workforce Recruitment & Development

- Each game in NSW to have an appointed and accredited Match Official

- Match Officials to Player ratio of 30:1 – baseline 56:1

- Coach to Player ratio of 10:1 – baseline 13:1

- Improve sideline and player behaviour with 25% reduction in Match Official abuse cases – baseline 73 cases

- Grow accredited Match Officials by 75% - baseline of 1,281 match officials

- Grow accredited coaches by 50% - baseline of 3,514 coaches

- Deliver yearly workforce conference with Net Promotor Score from attendees > 75

- Increase number of referees from underrepresented groups; female, Pasifika and First Nations Match Officials – baseline 106 females, 80 Pasifika and 13 First Nations Match Officials

- Reduce churn by 1% p.a. in workforce numbers – baseline 39.5%

- Schools Rugby & Get into Rugby Activations

- Establish 5 x schools support and Get into Rugby hubs with a minimum of 20 participants at each program:

  - Upper South Coast

  - Lower South Coast

  - Snowy Hub

  - Monaro Hub

  - Riverina Hub

Pillar 4: Inclusion

- Female Programs

- New Female Programs and Competitions across NSW (see competition seed-funding)

- Girls Tri Tag program in Griffith and Wagga Wagga – expanding to four locations by 2027

- Yearly ‘Rising Star’ talent combine in Southern NSW with 20+ girls involved each year

- Female coach development program – 50+ female coaches each year

- 150% growth in female coaches – baseline of 192 accredited female coaches

- 200% growth in female match officials – baseline of 106 accredited female Match Officials

- 50% growth in female participation – baseline of 7,917 club players, 3,642 event players, 16,803 school participants

- First Nations

- Deliver NSWRU Reconciliation Action Plan

- Deliver 6 x Talent ID workshops annually (North Coast, Central West, Sydney Metro, South Coast, 2 x Southern Inland)

- Deliver NSW First Nations Development Academy

- Pasifika

- Launch yearly Pasifika Leadership program with 20+ attendees each year

- Grow attendance at Pasifika Youth Cup by 50%

- Integrity & Safeguarding activity

- All Rugby clubs in NSW compliant against RA integrity and safeguarding standards

- Deliver 6 x yearly safeguarding and integrity workshops

Pillar 5: RWC Activation

- Deliver 20 x RWC Event Hubs during & post RWC with a minimum of 50 participants. Each hub to contain:

  - Get into Rugby

  - Tri Tag Rugby

  - Coach education

  - Match Official education

- RWC Event Hubs to be spread across metro & regional NSW to ensure everyone has an opportunity to be involved in the Rugby World Cup.

# Project Plan

# Pillar 1: Facilities and Equipment

| Initiative | Key Activities | Responsible Organisation/Team | Due Date | Status update |
| --- | --- | --- | --- | --- |
| RWC Infrastructure Grants Program | -Open infrastructure program addressing the key priorities: (a) female friendly facilities, and accessible facilities (b) lighting (c) sustainable practises e.g. adequate drainage and irrigation | Managed by OoS Smarty Grants – supported by RA, NSWRU, ACT/SNSWRU | Launch R1 EO 2025. Close R3 Jan 2028. |  |
| RWC Equipment Grants Program | -Deliver a major equipment grant program for high-cost safety and Rugby equipment such as scrum machines | Managed by OoS Smarty Grants – supported by RA, NSWRU, ACT/SNSWRU | Launch R1 EO 2025. Close R3 Jan 2028. |  |
| Targeted Priority Infrastructure Investment (NSW) | -Priority infrastructure fund for key strategic priority in NSW | NSWRU & RA | Confirmation of venue 2025. Distribution EO 2026. |  |
| Targeted Priority Infrastructure Investment (SNSW) | - Priority infrastructure fund for key strategic priority in Southern NSW | ACT/SNSWRU & RA | Distribution EO 2026. |  |

# Pillar 2: Priority Regions & Pathways

| Initiative | Key Activities | Responsible Organisation/Team | Due Date | Status update |
| --- | --- | --- | --- | --- |
| Western Sydney GM (co-funded by RA) | -Appoint Head of Western Sydney -Manage strategic and operational direction for Western Sydney -Manage Western Sydney Academy -Work with Club Development Manager to lead club strategic direction -Launch Western Sydney Rugby alliance (clubs, schools, referees, affiliates) | NSWRU / RA | October 2025 |  |
| Western Sydney CDM (co-funded by RA) | -Appoint Western Sydney Club Development Manager -Increased Club Development support to improve existing clubs and develop new clubs where required. -Support clubs to reach governance standards. -Support clubs with their attainment of 40:40:20 Governance model -Deliver yearly Club Health Check for each W. Syd club -Deliver yearly Club Development workshops -Deliver Action Plans for each club -Deliver appropriate training, education and assistance | NSWRU / RA | October 2025 |  |
| Western Sydney DO (co-funded by NSWRU) | -Appoint Western Sydney Development Officer -Deliver Western Sydney Schools programs -Connect Western Sydney schools with local clubs -Attend club training sessions -Deliver coaching course in Western Sydney -Support junior clubs with recruitment and retention of players, coaches and match officials -Convert exposure/sampling opportunities in gala days and programs into regular club rugby participants | NSWRU | October 2025 |  |
| Western Sydney Competitions | -Seed-fund new, and grow existing competitions in Western Sydney across clubs and schools in both contact and non-contact formats -Develop new Schools competition including Western Sydney Waratah Shield Division, U16 and Primary school competition for boys and girls | NSWRU | First investment Jan 2026 |  |
| Western Sydney Academy | -Develop a Western Sydney academy to assist pathway development -Identify talent in Western Sydney to join Academy | NSWRU | First intake Jan 2026 |  |
| Hunter R4G Manager (co-funded by NSWRU) | -Appoint Hunter Rugby for Good General Manager -Lead the Rugby for Good program in the Hunter -Secure additional funding to deliver Rugby for Good activity in the -Hunter region including Rucky Tackle Life, Rugby for Good Mental Health Programs, Our Turn, Your Time Women’s program | NSWRU | October 2025 |  |
| Hunter R4G Activity | -Club Development activity in the Hunter -Competition and program support in the Hunter -Deliver programs and provide opportunities that enhance, support and build rugby communities -Complete Club Health audit for Hunter Rugby clubs -Deliver Action Plans for each club | NSWRU | Ongoing 2025 - 2028 |  |

# Pillar 3: Programs & Workforce

| Initiative | Key Activities | Responsible Organisation/Team | Due Date | Status update |
| --- | --- | --- | --- | --- |
| Competition Seed-Funding Grants Program | -Deliver a targeted competition grants program to seed-fund competition launch and expansion: *New & expanded competitions targeting regional areas, youth programs, female programs, inclusion programs and non-contract programs * Starter kits & equipment grants *Operational support including subsidising technology to decrease volunteer burden, Match Officials, travel, field hire *Promotional campaigns to drive engagement and awareness among targeted communities *Training and support for key administrators and club people to increase capability and capacity and decrease the burden on volunteers | Managed by OoS Smarty Grants – supported by RA, NSWRU, ACT/SNSWRU | Launch R1 EO 2025. Close R3 Jan 2028. |  |
| Workforce Recruitment & Development | -Coach and match official education for underrepresented groups (see female, First Nations and Pasifika activity) -Volunteer recruitment and club development programs -Volunteer rewards and recognition programs and opportunities at the RWC 27 -Workforce recruitment for coaches, match officials and administrators -Sustainable club activity – delivering education, training and assistance | NSWRU | Ongoing – 2025 – 2028 |  |
| Match Official Manager (co-funded by NSWRU) | -Appoint NSW Match Official Manager -Lead NSW MO strategy and operational planning -Deliver Match Official workshops and mentoring programs -Implement MO development program -Deliver on recruitment campaigns focused on female referees -Promote improved sideline behaviour through ongoing education and sanction process -Targeted recruitment focusing on recently retired players -Club/Hub based programs to bring MO’s to younger age groups -Increased access to equipment and filming resources for MO’s | NSWRU | October 2025 |  |
| Workforce Leadership Program & Conference | -Deliver yearly workforce leadership program for coaches, match officials and administrators -Support growth and development of underrepresented groups in the workforce including Pasifika communities, First Nations and Females | NSWRU, ACT/SNSWRU & RA | Yearly – 2026, 2027, 2028 |  |
| Schools Rugby & Get into Rugby Activations | -Implementation of school’s rugby programs and regional Get into Rugby hubs to drive engagement in 5–17-year-olds | ACT/SNSWRU | Ongoing 2025 - 2028 |  |

# Pillar 4: Inclusion

| Initiative | Key Activities | Responsible Organisation/Team | Due Date | Status update |
| --- | --- | --- | --- | --- |
| Female Participation Officer (NSW) (co-funded by NSWRU) | -Appoint Female Participation Officer in NSW -See below in Female Programs and Support | NSWRU | October 2025 |  |
| Female Participation Officer (SNSW) (co-funded by ACT/SNSWRU) | -Appoint Female Participation Officer in SNSW -See below in Female Programs and Support | ACT/SNSWRU | October 2025 |  |
| Female Programs and Support (NSW) | -Introductory participation programs -New competitions -Talent/ pathway programs -Coach development and Match Officials programs -Club development and support, increasing the number of women in administration and leadership positions withing NSW rugby. | NSWRU | Ongoing 2025 - 2028 |  |
| Female Programs and Support (SNSW) | -Introductory participation programs -New competitions -Talent/ pathway programs -Coach development and Match Officials programs -Club development and support, increasing the number of women in administration and leadership positions withing NSW rugby. | ACT/SNSWRU | Ongoing 2025 - 2028 |  |
| Female programs branding, collateral and activations | -Supporting materials for clubs to promote best practice e.g. posters, online materials, social media posts, etc. | RA | Ongoing 2025 - 2028 |  |
| First Nations Development Officer (NSW) (co-funded by NSWRU) | -Appoint First Nations Development Officer -Deliver First Nations activity in NSW (see below) | NSWRU | October 2025 |  |
| First Nations Activity (NSW) | -Host regional and metro talent ID days in NSW to transition talent into high performance pathways. -First Nations Development Academy -Work with Lloyd McDermott Rugby to develop a First Nations Leadership program aligned with U16 boys’ and girls’ programs -First Nations mentoring programs -Bursary places for First Nations coaches -Deliver NSWRU RAP | NSWRU | Ongoing 2025 - 2028 |  |
| First Nations Activity (SNSW) | -Host regional and metro talent ID days in NSW to transition talent into high performance pathways. -First Nations Development Academy -Work with Lloyd McDermott Rugby to develop a First Nations Leadership program aligned with U16 boys’ and girls’ programs -First Nations mentoring programs -Bursary places for First Nations coaches | ACT/SNSWRU | Ongoing 2025 - 2028 |  |
| Pasifika & First Nations Leadership Activity | -Leadership and support programs for Pasifika and First Nations people -Work with Lloyd McDermott Rugby to develop a First Nations Leadership program aligned with U16 boys’ and girls’ programs -First Nations mentoring programs -Bursary places for First Nations and Pasifika coaches | NSWRU | Ongoing 2025 - 2028 |  |
| Pasifika Programs | -Enhance existing and develop new Pasifika events and tournaments for children and adults -Deliver Pasifika Leadership program | NSWRU | Ongoing 2026 - 2028 |  |
| All Abilities programs & support | -Enhance existing and develop new partnerships and programs to support people with a disability to engage in Rugby | NSWRU & RA | Ongoing 2026 - 2028 |  |
| Pride programs & support | -Enhance existing and develop new partnerships and programs to support and celebrate the Pride community in Rugby | NSWRU & RA | Ongoing 2026 - 2028 |  |
| Integrity & Safeguarding Manager (co-funded by NSWRU) | -Appoint NSW Integrity & Safeguarding manager | NSWRU | October 2025 |  |
| Integrity & Safeguarding activity | -Audit of Rugby clubs safeguarding, integrity and data management practices (RA Club Health Check) -Identify priority clubs and areas of support following audit -Provide additional and focused training for staff, volunteers and administrators on dealing with integrity and safeguarding matters -Focus on compliance with National, State and local laws, regulations and policies -Improve supporting technology to track WWCC, training completions and incident reporting via Rugby Xplorer -Supporting materials for clubs to promote best practice e.g. posters, online materials, social media posts, etc. | NSWRU | Ongoing 2025 - 2028 |  |

# Pillar 5: RWC Activation

| Initiative | Key Activities | Responsible Organisation/Team | Due Date | Status update |
| --- | --- | --- | --- | --- |
| RWC Post-Event Hubs Delivery & Management | RWC Event Hubs to provide Rugby opportunities during and immediately post the RWC to capture interest in the sport while it is at its peak. This includes: -Get into Rugby (4–7-year-olds) -Tri Tag Rugby – non-contact version of the game suitable for 7 – 97 years of age -Match Officials programs -Coaching programs | RA led, activations by NSWRU & ACT&SNWRU | 30/11/2027 |  |
| RWC Post-Event Hub Giveaways | RWC event activation will also include giveaways to prospective participants at matches and in fan-zones to drive a call to action to participate in the sport. | RA | 30/09/2027 |  |

# Project Management, Monitoring & Evaluation

| Initiative | Key Activities | Responsible Organisation/Team | Due Date | Status update |
| --- | --- | --- | --- | --- |
| Monitoring & Evaluation | Implement robust monitoring and evaluation process including key social impact measurables, impact reporting and key outcomes. | RA | Ongoing. 2025 baseline measurements. Yearly impact check-in. Final report July 2028. |  |
| Project Management | Overall day-to-day project management and oversight and delivery of the legacy program including, but not limited to: -Lead monitoring & evaluation -Grant submission, variation, reporting, communication -Financial management and oversight -Central point of contact | RA | Ongoing 2025 - 2028 |  |

- Appendix. Rugby Australia Club Standards Program

The below link and description relate to the Rugby Australia National Club Standards program to support and drive Club Development across the country.

The Rugby Australia National Club Standards Framework aims to provide the 650+ community rugby clubs and their committees with:

  - A greater understanding of their current off-field operational position, and

  - The ability to measure/compare against a consistent framework to support greater Club Development.

The NCSF is aligned with the current Rugby Australia Strategy 2025-2029 pillar for participation growth and supports the development of healthy, vibrant and sustainable clubs to ensure a high quality rugby experience for players, spectators, volunteers and the broader community.

The National Club Standards Framework will allow clubs to gain a greater understanding of their priorities, strengths, and areas of required support.

Clubs will be supported in the attainment of these standards by the Rugby Australia Club Development team.

https://d26phqdbpt0w91.cloudfront.net/NonVideo/170460ab-426c-4cb7-a9d4-1e126b6cb242.pdf

Appendix 3. Reporting Dashboards

Below are some examples of the dashboards Rugby Australia are able to create to visualise the impact of the Office of Sport Rugby World Cup Legacy Investment.

*This example is for illustrative purposes only and doesn’t accurately reflect current participation data in NSW.

- Appendix 4. Western Sydney Prioritisation Report

The below link is an example of reports Rugby Australia has conducted into Western Sydney, prioritising and exploring in depth, the four LGA’s of Canterbury-Bankstown, Fairfield, Liverpool, and Penrith with the aim of identifying the highest priority rugby development suburbs.

https://d26phqdbpt0w91.cloudfront.net/NonVideo/5ac2ea5e-44dc-4199-8d9c-5c2b3b54b0d5.pdf

| Office of Sport |  |
| --- | --- |
| Level 3, 6B Figtree Drive, Sydney Olympic Park, NSW 2128 Locked Bag 1422, Silverwater NSW 2128 | Office hours: Monday to Friday 9.00am — 5.00pm T: 13 13 02 E: email@sport.nsw.gov.au W: sport.nsw.gov.au |